## Slide 1
Stephen W. Meador, Chairperson
DOE/SC Review Committee
Office of Science, U.S. Department of Energy
http://www.science.doe.gov/opa/
Closeout Report for the
National Spherical Torus
Experiment (NSTX) Upgrade Project
Princeton Plasma Physics Laboratory
May 2-3, 2012

## Slide 2: Review Committee Participants
Stephen Meador, DOE/SC, Chairperson
Subcommittee 1: Technical Observers
*Arnie Kellman, General Atomics Barry Sullivan, DOE/SC
David Lissauer, BNL Jeff Makiel, DOE/PSO
Subcommittee 2: Cost and Schedule
*Ray Won, DOE/SC
Tim Maier, DOE/BHSO
Ethan Merrill, DOE/SC
Subcommittee 3: Management
*Frank Crescenzo, DOE/BHSO
Mike Epps, DOE/TJSO
*Lead

## Slide 3: Charge Questions
Construction Efforts: Are construction efforts being executed safely? Does the project have adequate resources and the appropriate skills mix to execute the project per the plan?
Baseline Cost and Schedule: Are the current project cost and schedule projections consistent with the approved baseline cost and schedule? Is the contingency remaining adequate for the risks that remain?
Management: Evaluate the management structure as to its adequacy to deliver the scope within budget and schedule. Are risks being actively managed? Has the project responded satisfactorily to the recommendations from the previous SC project review?
Earned Value Management (EVM): Has Princeton University/ PPPL implemented all required actions in the Corrective Action Plan that was developed following the EVM System certification review from October 2011?

## Slide 4: Report Outline/Writing Assignments
Executive Summary Meador
1. Introduction Sullivan
2. Technical Status (Charge Questions 1, 3) Kellman*/Lissauer
2.1 Findings
2.2 Comments
2.3 Recommendations
3. Cost and Schedule (Charge Question 2, 3, 4) Won*/Maier/Merrill
4. Management and ES&H (Charge Questions 1, 3, 4) Crescenzo*/Epps
*Lead

## Slide 5: 2. Technical Status Kellman, GA; Lissauer, BNL
Construction Efforts: Are construction efforts being executed safely? Does the project have adequate resources and the appropriate skills mix to execute the project per the plan?
Yes. The construction efforts are being executed safely. The project appears to have adequate resources and the necessary skill mix to execute both the baseline and the 6 month “accelerated” schedule. Potential conflicts with other lab projects for analysts have been resolved and the project has addressed a predicted need for additional welders.
Management: Evaluate the management structure as to its adequacy to deliver the scope within budget and schedule. Are risks being actively managed? Has the project responded satisfactorily to the recommendations from the previous SC project review?
The project management is well structured to deliver the scope within budget and schedule. Risks are being actively managed and the project has responded satisfactorily to all of the technical recommendations of the previous SC review. There are no significant outstanding technical issues that need to be resolved.

## Slide 6: 2. Technical Status Kellman, GA; Lissauer, BNL
Findings
  There have been no reportable accidents on the NSTX-U project.
  A safety incident with serious injury at PPPL is being thoroughly investigated by the lab and lessons learned are being transferred to the NSTX-U project.
  A fully resource- loaded schedule for both the baseline and 6-month accelerated schedule has been prepared. Analysis for all necessary skill mixes are reviewed by management. Past and predicted resource conflicts have been addressed and with present funding profile, adequate staff is available to complete the project on the accelerated schedule.
  Risks are actively managed and updated monthly by the CAMs.

## Slide 7: 2. Technical Status Kellman, GA; Lissauer, BNL
  Recommendations of CD-3 and earlier reviews have been adopted:
    A plan has been developed to measure halo currents and VV displacements. Implementation is well underway with parts on-hand or delivery expected well before the need date.
    Evaluation of spare key fabrication tools (e.g. induction welder or VPI oven heaters) was performed. It was determined that expected vendor repair times and readily available spare parts eliminated the need to purchase spare units.
    CAMAC hardware on the NB LCC is being replaced by more modern National Instruments hardware using LABVIEW.
    A large scale test of the Aquapour removal in the CS is scheduled for this summer.
  The NBI project is technically sound and is progressing well. The task is under cost and ahead of the accelerated schedule. Task is not critical path.

## Slide 8: 2. Technical Status Kellman, GA; Lissauer, BNL
  Development of the friction stir welding procedures and Non-Destructive Testing have been completed with 4 conductors delivered. Excellent progress has been made on the technique for soldering the cooling tube into the TF conductor and the first conductor has been soldered.
  The Digital Coil Protection System (DCPS) algorithm has been significantly simplified and software FDR is schedule for July 2012. Analysis of all 96 disruption cases have qualified the TF torsional shear.
  All ancillary systems are on schedule, with no technical or procurement problems.

## Slide 9: 2. Technical Status Kellman, GA; Lissauer, BNL
Comments
  The safety culture on the NSTX-U project is excellent and a serious concern for safety is evident at all levels of the project team from upper lab management to the field technicians. The safety organization, personnel, training and procedures appear well suited to being able to perform the NSTX-U project with minimum risk to staff.
  The safety incident on the Skid steer at PPPL is prompting the lab to review many of its procedures and practices. In that spirit, we suggest that they consider expanding their stationary power tool training and qualification program to other more portable, but also potentially dangerous tools, e.g. portable power tools and hand-held hydraulic tools (punch, crimpers).
  Continue to examine equipment tooling needs for critical path fabrication and assembly tasks and consider purchasing sufficient in-house spare to minimize down-time.

## Slide 10: 2. Technical Status Kellman, GA; Lissauer, BNL
  Although the NB project is progressing smoothly and most technical issues are resolved, significant attention needs to be maintained on the vacuum vessel cutting, port fabrication by the vendor, and port installation. We suggest that this be added to the risk registry.
  While there appears to be sufficient time between the large scale Aquapour test this summer and the actual need date to resolve any technical issues that might arise from the test, we feel that the uncertainty of the test should be on the registry.
  Given the critical nature of the entire CS fabrication task, we believe that the risk registry should recognize specific risks, especially schedule risks associated with the remaining major procurements (OH conductor, Inconel casing, OH mold), tooling, machines, and fabrication techniques (VPI, inductor brazing). In addition, discussion of near-critical path items and mitigation plans should be presented or provided as supplemental material in the next status review.

## Slide 11: 2. Technical Status Kellman, GA; Lissauer, BNL
  The project consider building five TF quadrants and selecting the best four for final assembly. Evaluate the cost, schedule, and risk impact. Is there a significant reduction in schedule impact if the fifth quadrant is planned rather than performed after a possible failure?
  While there are no specific recommendations, it is our observation that project delays are often the result of problems with more mundane, low tech systems such as power supplies and water systems. For NSTX-U, the new PF-coils, reused cables and fibers might also fall into this category. We encourage the project team to pay adequate attention to these items as well as the more complex R&D issues.
  Continue to track the full Thomson scattering system task including any in-vessel calibration on the project schedule even though only the vacuum part is in the project scope.

## Slide 12: 2. Technical Status Kellman, GA; Lissauer, BNL
Recommendations
  Review and update the risk registry to more completely reflect items (mentioned in comments) that are on the critical path or near-critical paths.

## Slide 13: 3. Cost and Schedule Won, DOE/SC; Maier, DOE/BHSO; Merrill, DOE/SC
Baseline Cost and Schedule: Are the current project cost and schedule projections consistent with the approved baseline cost and schedule? Yes.
Is the contingency remaining adequate for the risks that remain? Yes
Findings
  Cost projections are consistent with the approved baseline and cost projections at CD-2, plus Engineering Change Proposals, including ECP-004.
  Schedule projections are managed to an accelerated schedule.
  CPI performance is 1.01 at 40% complete and anticipated to continue overall.
  SPI performance is 1.09 and continued acceleration is planned to available funding.
  Schedule acceleration increases float from 12 to 18 months.
  Cost Contingency is reported as $15.1M, or 32% of to go costs, up from 30% of to go costs at CD-3, and is back-end loaded under the accelerated schedule.
  The Risk Registry documents $4.7M of open risks.
    Risks from reduced funding and unknown-unknowns are not identified.

## Slide 14: 3. Cost and Schedule Won, DOE/SC; Maier, DOE/BHSO; Merrill, DOE/SC
Baseline Cost and Schedule (cont’d)
    Critical Path continues to run through conductor deliveries, Center Stack fabrication, and Center Stack installation
Comments
  Schedule acceleration reduces standing army costs, and active risks and advances the Fusion Energy research schedule.
  Cost Contingency outlays would be needed to fund schedule stretch under budget guidance constraints (Standing Army Costs ~$250K/month).
    Estimated Cost Contingency: approx. 17% at the beginning of FY14.
  An updated risk identification/assessment and scope contingency plan (additive/deductive) to address funding uncertainties is considered critical.
Recommendations
  Review the risk registry/assessment and scope contingency plan to ensure they are complete and up to date.

## Slide 15: 3. Cost and Schedule Won, DOE/SC; Maier, DOE/BHSO; Merrill, DOE/SC
Management: Evaluate the management structure as to its adequacy to deliver the scope within budget and schedule. Are risks being actively managed? Yes, from a Cost and Schedule Perspective
  Has the project responded satisfactorily to the recommendations from the previous SC project review. Yes, from a Cost and Schedule Perspective
Findings
  Scope delivery is on target and schedule delivery is ahead of plan.
  The accelerated schedule helps to retire risks early and boost effectiveness.
  The project and program have discussed contingency use for accelerated schedule and scope alternatives.
  Contingency impact from schedule acceleration is quantified.

## Slide 16: 3. Cost and Schedule Won, DOE/SC; Maier, DOE/BHSO; Merrill, DOE/SC
Management: (cont’d)
Comments
    Importance of maintaining the risk registry/assessment and scope contingency plan is discussed in the response to Charge 2.
Recommendations
  None

## Slide 17: 3. Cost and Schedule Won, DOE/SC; Maier, DOE/BHSO; Merrill, DOE/SC
Earned Value Management (EVM): Has Princeton University/ PPPL implemented all required actions in the Corrective Action Plan that was developed following the EVM System certification review from October 2011? YES
FINDINGS
  PU/PPPL has implemented the corrective actions necessary to satisfy the intent of Corrective Action Requests (CAR) 1-4 and Continuous Improvement Opportunities (CIO) 1-6

## Slide 18: 3. Cost and Schedule Won, DOE/SC; Maier, DOE/BHSO; Merrill, DOE/SC
Comments
  CAR #1 has been implemented by Engineering Change Proposal #4 and the project continuing to evaluate the need for changes to the Performance Measurement Baseline;
  The System Description has been updated to address the preparation of Variance Analysis Reports (CAR #2) and the current Control Account Manager (CAM) Training Program satisfies the requirement for a training procedure. The Office of Project Assessment and PU/PPPL will evaluate the need to change the variance thresholds in the Project Execution Plan.
  The schedule has been thoroughly reviewed and updated in response to CAR #3 and the number of constrained activities has been reduced to approximately 5%.
  Based on discussions, it appears the CAMs have taken a proactive role in the EVMS and baseline management process.
  PU/PPPL is encouraged to continue their diligent implementation of EVM processes.
Recommendations
  None

## Slide 19: Project Status Won, DOE/SC; Maier, DOE/BHSO; Merrill, DOE/SC
PROJECT STATUS as of March 31, 2012 |  | 
Project Type | MIE | 
CD-1 | Planned: January 2010 | Actual: April 2010
CD-2 | Planned: October 2010 | Actual: December 2010
CD-3 | Planned: January 2012 | Actual: December 2011
CD-4 | Planned: September 2015 | Actual:
TPC Percent Complete | Planned: _36.8% | Actual: _40_%
TPC Cost to Date | $31.4 M | 
TPC Committed to Date | $33.6 M | 
TPC | $94.3 M | 
TEC | $83.5 M | 
Contingency Cost (w/Mgmt Reserve) | $15.7 M | 33% to go
Contingency Schedule on CD-4 | 12 months | 41__%
CPI Cumulative | 1.01 | 
SPI Cumulative | 1.09 | 

## Slide 20: 4. Management and ES&H Crescenzo, DOE/BHSO; Epps, DOE/TJSO
Construction Efforts: Are construction efforts being executed safely? Yes Does the project have adequate resources and the appropriate skills mix to execute the project per the plan? Yes
Management: Evaluate the management structure as to its adequacy to deliver the scope within budget and schedule. Are risks being actively managed? Yes. Has the project responded satisfactorily to the recommendations from the previous SC project review? Yes.
Earned Value Management (EVM): Has Princeton University/ PPPL implemented all required actions in the Corrective Action Plan that was developed following the EVM System certification review from October 2011? Yes.

## Slide 21
Findings
  The management team has been stable since baseline approval and authorization to begin construction.
  The project is forecasting six month accelerated early finish relative to the baseline early finish.
  Procurements are proceeding well; critical vendors are delivering mostly to plan.
  Fabrication of major technical components (center stack, neutral beam, ancillary systems) report excellent progress with no major technical complications or significant risks on the horizon.
  Installation and construction reports excellent progress with “disassembly” nearly complete and labor costs lower than estimated.
4. Management and ES&H Crescenzo, DOE/BHSO; Epps, DOE/TJSO

## Slide 22
  There are no project related recordable injuries or significant radiological incidents to date.
  The President’s 2013 requested budget jeopardizes the accelerated schedule plan.
  There may be significant impacts to the project resulting from possible funding reductions at the lab.
  Preliminary out-year funding projections negatively impact the baseline early finish date, budget at completion, cost contingency and risk.
  The University Advisory Committee visited the lab in late April and reviewed the project along with other programs at the lab. There were no project sponsored peer reviews since CD-3.
  There is renewed emphasis on safety at the Lab in general, and on the project, resulting from an injury at the Lab in March.
4. Management and ES&H Crescenzo, DOE/BHSO; Epps, DOE/TJSO

## Slide 23
Comments
  The project has performed very well since CD-3 as measured by EVMS data.
  The project appears on track to successful early completion based on performance to date, remaining cost and schedule contingencies, and risk analysis.
  Installation and construction appear very well planned and executed so far.
  Safety performance is adequate.
4. Management and ES&H Crescenzo, DOE/BHSO; Epps, DOE/TJSO

## Slide 24
Comments
  Proposed impacts to the project from the President’s FY-2013 budget and preliminary out-year funding projections have not been fully analyzed and appear unacceptable to the committee as presented in early analysis (17% back loaded contingency, 6 mos. float).
  Program, Project and Site Office must carefully evaluate all impacts to the baseline from potential changes to funding profiles once these are better understood and communicated by the program.
  There is no comprehensive strategy, agreed to by PPPL, Site Office, and Program to address the funding uncertainties.
4. Management and ES&H Crescenzo, DOE/BHSO; Epps, DOE/TJSO

## Slide 25: 4. Management and ES&H Crescenzo, DOE/BHSO; Epps, DOE/TJSO
Recommendations
  Program, Project, Laboratory and Site Office develop a strategy to address impacts from potential changes in the funding profile.