## Report
| Current Period | [6 empty] | Cumulative to Date | [8 empty] | At Complete
WBS OBS | Budget | Actuals | Earned | SV | CV | SPI | CPI | Budget | Actuals | Earned | SV | CV | SPI | CPI | TCPIbac | TCPIeac | BAC | EAC | VAC | % Spent | % Complete
1.1 Torus Systems | 380.8211 | 550.9028 | 223.8425 | -156.9786 | -327.0603 | 0.58779 | 0.40632 | 23564.3159 | 25980.458 | 22013.4105 | -1550.9054 | -3967.0475 | 0.93418 | 0.84731 | -2.506 | 0.80797 | 24848.971 | 29489.9434 | -4640.9724 | 88.1% | 88.59%
1000 CSU Analytical Support (Dudek) | 13.6118 | 32.6197 | 13.6118 | 0 | -19.0079 | 1 | 0.41729 | 552.5808 | 574.6559 | 552.5808 | 0 | -22.0751 | 1 | 0.96159 | 1.169 | 0.99807 | 705.2855 | 727.656 | -22.3705 | 78.97% | 78.35%
1001 CS Plasma Facing Components (Tresemer) | 26.4733 | 36.1752 | 27.2487 | 0.7754 | -8.9265 | 1.0293 | 0.75324 | 2064.8486 | 1778.4151 | 1959.4976 | -105.351 | 181.0825 | 0.94898 | 1.1018 | 0.45387 | 1.0033 | 2109.9886 | 1928.4151 | 181.5735 | 92.22% | 92.87%
1002 Passive Plate Analysis & Upgrade (Atnafu) | 6.5198 | 26.1017 | 24.0393 | 17.5195 | -2.0624 | 3.6871 | 0.92099 | 722.049 | 566.0384 | 744.5443 | 22.4953 | 178.5059 | 1.0312 | 1.3154 | 0.58496 | 0.99836 | 996.1321 | 818.0383 | 178.0938 | 69.19% | 74.74%
1200 Structures & Supports (Smith) | 1.3781 | 60.7549 | 0 | - | - | 0 | 0 | 3790.5197 | 4467.5672 | 3773.3597 | -17.16 | -694.2075 | 0.99547 | 0.84461 | -0.025345 | 0.46378 | 3790.5197 | 4504.5672 | -714.0475 | 99.18% | 99.55%
1300 Center Stack (Chrzanowski) | 60.4001 | 111.3698 | 60.4001 | 0 | -50.9697 | 1 | 0.54234 | 2341.4438 | 2667.2164 | 2341.4438 | 0 | -325.7726 | 1 | 0.87786 | 16.9808 | 0.99757 | 2687.6017 | 3014.2164 | -326.6147 | 88.49% | 87.12%
1301 Outer TF Coils (CLOSED) | 0 | 0 | 0 | - | - | - | - | 470.5301 | 476.7041 | 470.5301 | 0 | -6.174 | 1 | 0.98705 | 0 | - | 470.5301 | 476.7041 | -6.174 | 100% | 100%
1302 Center Stack Assembly (Chrzanowski) | 0 | 0 | 0 | - | - | - | - | 683.607 | 171.5831 | 235.8912 | -447.7158 | 64.3081 | 0.34507 | 1.3748 | 0.90444 | 0.90038 | 844.5448 | 847.5831 | -3.0383 | 20.24% | 27.93%
1303 TF Joint Test Stand & Test (CLOSED) | 0 | 0 | 0 | - | - | - | - | 352.8769 | 225.084 | 352.8769 | 0 | 127.7929 | 1 | 1.5678 | 0 | 0 | 352.8769 | 224.5695 | 128.3074 | 100.2% | 100%
1304 Inner TF Bundle (Chrzanowski) | 186.6903 | 9.6906 | 41.58 | -145.1103 | 31.8894 | 0.22272 | 4.2908 | 3417.0755 | 3230.0016 | 3139.6634 | -277.4121 | -90.3382 | 0.91882 | 0.97203 | 1.2691 | 0.7993 | 3565.6878 | 3763.0016 | -197.3138 | 85.84% | 88.05%
1305 Ohmic Heating Coil (Chrzanowski) | 78.4924 | 248.6766 | 37.3109 | -41.1815 | -211.3657 | 0.47534 | 0.15004 | 6520.2935 | 9265.3005 | 5975.1035 | -545.19 | -3290.197 | 0.91639 | 0.64489 | -0.27069 | 0.60008 | 6675.9937 | 10433.3004 | -3757.3067 | 88.81% | 89.5%
1306 Inner PF Coils (Chrzanowski) | 0 | 25.0956 | 19.6517 | 19.6517 | -5.4439 | - | 0.78307 | 824.078 | 831.364 | 714.3475 | -109.7305 | -117.0165 | 0.86684 | 0.85925 | -15.0605 | 0.89943 | 824.078 | 953.364 | -129.286 | 87.2% | 86.68%
1307 CS Casing Assembly (Chrzanowski) | 7.2553 | 0.4187 | 0 | - | - | 0 | 0 | 1382.495 | 1284.6088 | 1311.6537 | -70.8413 | 27.0449 | 0.94876 | 1.0211 | 0.72738 | 1.0022 | 1383.8141 | 1356.6088 | 27.2053 | 94.69% | 94.79%
1310 CSU Magnets Systems (CLOSED) | 0 | 0 | 0 | - | - | - | - | 441.918 | 441.9189 | 441.918 | 0 | -0.0009 | 1 | 1 | 0 | - | 441.918 | 441.9189 | -0.0009 | 100% | 100%
1.2 Plasma Heating and Current Drive Systems | 396.9515 | 431.9704 | 365.6324 | -31.3191 | -66.338 | 0.9211 | 0.84643 | 19433.8857 | 17583.1624 | 18640.7224 | -793.1633 | 1057.56 | 0.95919 | 1.0601 | 0.82509 | 1.0001 | 23629.4062 | 22571.5398 | 1057.8664 | 77.9% | 78.89%
2300 ECH Analysis (CLOSED) | 0 | 0 | 0 | - | - | - | - | 84.1986 | 28.7168 | 84.1986 | 0 | 55.4818 | 1 | 2.932 | 0 | 0 | 84.1986 | 29.0946 | 55.104 | 98.7% | 100%
2420 2nd NBI Sources (CLOSED) | -254.36 | 0 | 0 | - | - | 0 | - | 99.1954 | 61.3631 | 99.1954 | 0 | 37.8323 | 1 | 1.6165 | 0 | - | 99.1954 | 61.3631 | 37.8323 | 100% | 100%
2425 BL Relocation (Cropper) | 0 | 1.8545 | 0 | - | - | - | 0 | 1802.8764 | 1217.0899 | 1694.4549 | -108.4215 | 477.365 | 0.93986 | 1.3922 | 0.18509 | 1.0039 | 1802.8764 | 1325.0899 | 477.7865 | 91.85% | 93.99%
2430 2nd NBI Decontamination (CLOSED) | 0 | 0 | 0 | - | - | - | - | 2057.0497 | 2069.9356 | 2057.0497 | 0 | -12.8859 | 1 | 0.99377 | 0 | - | 2057.0497 | 2069.9356 | -12.8859 | 100% | 100%
2440 2nd NBI Beamline (Cropper) | 0 | 0.7838 | 0 | - | - | - | 0 | 1978.776 | 1514.4656 | 1901.1671 | -77.6089 | 386.7015 | 0.96078 | 1.2553 | 0.16715 | 0.99499 | 1978.776 | 1592.4655 | 386.3105 | 95.1% | 96.08%
2450 2nd NBI Services (Cropper) | 81.8227 | 92.3797 | 13.0293 | -68.7934 | -79.3504 | 0.15924 | 0.14104 | 3764.4954 | 3406.1739 | 3872.7218 | 108.2264 | 466.5479 | 1.0287 | 1.137 | 0.69788 | 0.99973 | 4950.4345 | 4484.1738 | 466.2607 | 75.96% | 78.23%
2460 2nd NBI Armor (Tresemer) | 42.516 | 52.3274 | 22.2586 | -20.2574 | -30.0688 | 0.52353 | 0.42537 | 665.0206 | 939.3315 | 712.7587 | 47.7381 | -226.5728 | 1.0718 | 0.75879 | -0.26728 | 0.99555 | 760.5451 | 987.3315 | -226.7864 | 95.14% | 93.72%
2470 2nd NBI Power (Raki) | 328.4704 | 208.9129 | 298.7529 | -29.7175 | 89.84 | 0.90953 | 1.43 | 2443.8285 | 2083.1388 | 2198.8308 | -244.9977 | 115.692 | 0.89975 | 1.0555 | 0.9179 | 1.0004 | 3492.3004 | 3376.1388 | 116.1616 | 61.7% | 62.96%
2475 2nd NBI Controls (Cropper) | 76.1355 | 20.8403 | 6.0444 | -70.0911 | -14.7959 | 0.07939 | 0.29003 | 2249.4421 | 1414.6199 | 1721.8439 | -527.5982 | 307.224 | 0.76545 | 1.2172 | 0.74326 | 1.0005 | 2611.2557 | 2303.6199 | 307.6358 | 61.41% | 65.94%
2480 2nd NBI/TVPS Duct (Blanchard) | 31.1764 | 7.4748 | 25.5472 | -5.6292 | 18.0724 | 0.81944 | 3.4178 | 2043.0643 | 2291.4217 | 2033.3266 | -9.7377 | -258.0951 | 0.99523 | 0.88736 | -0.30735 | 0.99469 | 2094.0025 | 2352.4216 | -258.4191 | 97.41% | 97.1%
2485 Vacuum Pumping System (Blanchard) | 42.3448 | 0 | 0 | - | - | 0 | - | 190.0473 | 361.3876 | 298.6174 | 108.5701 | -62.7702 | 1.5713 | 0.82631 | 3.3837 | 1.0012 | 387.7205 | 450.3875 | -62.667 | 80.24% | 77.02%
2490 NTC Equipment Relocations (Perry) | 48.8457 | 47.397 | 0 | - | - | 0 | 0 | 2055.8914 | 2195.518 | 1966.5575 | -89.3339 | -228.9605 | 0.95655 | 0.89571 | 1.2052 | 1.0004 | 3311.0514 | 3539.518 | -228.4666 | 62.03% | 59.39%
1.3 Auxiliary Systems | 69.9584 | 13.6934 | 1.5821 | -68.3763 | -12.1113 | 0.022615 | 0.11554 | 266.832 | 239.2839 | 244.2048 | -22.6272 | 4.9209 | 0.9152 | 1.0206 | 0.97747 | 0.87501 | 457.7072 | 483.284 | -25.5768 | 49.51% | 53.35%
3200 Water Cooling System Mods (Atnafu) | 0 | 3.7056 | 1.5821 | 1.5821 | -2.1235 | - | 0.42695 | 74.1034 | 45.6934 | 72.5213 | -1.5821 | 26.8279 | 0.97865 | 1.5871 | 0.8206 | 0.80206 | 195.2367 | 198.6935 | -3.4568 | 23% | 37.15%
3300 Bakeout System Mods CSU (Raki) | 69.9584 | 8.82 | 0 | - | - | 0 | 0 | 90.4399 | 118.8201 | 115.6306 | 25.1907 | -3.1895 | 1.2785 | 0.97316 | 1.0771 | 0.99003 | 160.1818 | 163.8201 | -3.6383 | 72.53% | 72.19%
3400 Gas Delivery System Mods (Blanchard) | 0 | 1.1678 | 0 | - | - | - | 0 | 102.2887 | 74.7704 | 56.0529 | -46.2358 | -18.7175 | 0.54799 | 0.74967 | 1.6802 | 1.0051 | 102.2887 | 120.7704 | -18.4817 | 61.91% | 54.8%
1.4 Plasma Diagnostics | 20.4769 | 34.2275 | 34.0367 | 13.5598 | -0.1908 | 1.6622 | 0.99443 | 1992.724 | 2257.6137 | 1859.7772 | -132.9468 | -397.8365 | 0.93328 | 0.82378 | -2.0303 | 0.95538 | 2126.3284 | 2536.6136 | -410.2852 | 89% | 87.46%
4100 Center Stack Diagnostics (Kaita) | 0 | 23.2088 | 0 | - | - | - | 0 | 835.5896 | 694.8759 | 732.6218 | -102.9678 | 37.7459 | 0.87677 | 1.0543 | 0.73175 | 0.99969 | 835.5896 | 797.8759 | 37.7137 | 87.09% | 87.68%
4500 MPTS VV Modification (Labik) | 0 | 11.0187 | 16.4065 | 16.4065 | 5.3878 | - | 1.489 | 1136.6575 | 1562.7378 | 1107.8082 | -28.8493 | -454.9296 | 0.97462 | 0.70889 | -0.067709 | 0.70364 | 1136.6575 | 1603.7377 | -467.0802 | 97.44% | 97.46%
4501 Bay A and L RWM Coil (Labik) | 20.4769 | 0 | 17.6302 | -2.8467 | 17.6302 | 0.86098 | - | 20.4769 | 0 | 19.3472 | -1.1297 | 19.3472 | 0.94483 | - | 0.87444 | 0.99803 | 154.0813 | 135 | 19.0813 | 0% | 12.56%
1.5 Power Systems | 642.5367 | 317.4713 | 238.6801 | -403.8566 | -78.7912 | 0.37147 | 0.75182 | 8378.8864 | 6894.3267 | 6790.9131 | -1587.9733 | -103.4136 | 0.81048 | 0.985 | 1.0313 | 0.92805 | 10193.1598 | 10560.3266 | -367.1668 | 65.29% | 66.62%
5000 CSU Power Systems (Raki) | 491.1213 | 114.9819 | 106.7526 | -384.3687 | -8.2293 | 0.21737 | 0.92843 | 4736.8295 | 3037.6141 | 3712.9454 | -1023.8841 | 675.3313 | 0.78385 | 1.2223 | 0.74968 | 0.97285 | 5735.4914 | 5116.6142 | 618.8772 | 59.37% | 64.74%
5200 DCPS (Hatcher) | 58.5374 | 124.7819 | 67.5719 | 9.0345 | -57.21 | 1.1543 | 0.54152 | 2270.8212 | 2810.5175 | 1903.626 | -367.1952 | -906.8915 | 0.8383 | 0.67732 | -1.244 | 0.70811 | 2406.3828 | 3520.5174 | -1114.1346 | 79.83% | 79.11%
5501 Coil Bus Runs (Atnafu) | 92.878 | 77.7075 | 64.3556 | -28.5224 | -13.3519 | 0.6929 | 0.82818 | 1371.2357 | 1046.1951 | 1174.3417 | -196.894 | 128.1466 | 0.85641 | 1.1225 | 0.8725 | 0.99994 | 2051.2856 | 1923.195 | 128.0906 | 54.4% | 57.25%
1.6 Central Instrumentation & Control | 58.9525 | 14.8472 | 15.8219 | -43.1306 | 0.9747 | 0.26838 | 1.0656 | 464.3388 | 379.1916 | 412.04 | -52.2988 | 32.8484 | 0.88737 | 1.0866 | 0.94475 | 0.99941 | 973.709 | 941.1916 | 32.5174 | 40.29% | 42.32%
6100 Control Sys Data Acquisition (Sichta) | 58.9525 | 14.8472 | 15.8219 | -43.1306 | 0.9747 | 0.26838 | 1.0656 | 464.3388 | 379.1916 | 412.04 | -52.2988 | 32.8484 | 0.88737 | 1.0866 | 0.94475 | 0.99941 | 973.709 | 941.1916 | 32.5174 | 40.29% | 42.32%
1.7 Project Support & Integration | 198.9605 | 279.5011 | 192.514 | -6.4465 | -86.9871 | 0.9676 | 0.68878 | 12590.4495 | 11968.7414 | 12571.403 | -19.0465 | 602.6616 | 0.99849 | 1.0504 | 0.76313 | 0.94897 | 14512.9986 | 14014.7413 | 498.2573 | 85.4% | 86.62%
7100 Project Management & Integration (Strykowsky) | 99.76 | 110.4603 | 99.76 | 0 | -10.7003 | 1 | 0.90313 | 5416.5278 | 5684.1772 | 5416.5278 | 0 | -267.6494 | 1 | 0.95291 | 1.3677 | 0.89768 | 6412.0604 | 6793.1772 | -381.1168 | 83.67% | 84.47%
7200 Center Stack Management (Dudek) | 18.7536 | 15.9568 | 18.7536 | 0 | 2.7968 | 1 | 1.1753 | 1400.7976 | 1208.7044 | 1400.7976 | 0 | 192.0932 | 1 | 1.1589 | 0.53723 | 0.99999 | 1623.7958 | 1431.7044 | 192.0914 | 84.42% | 86.27%
7300 NB2 Management (Stevenson) | 21.8119 | 15.4661 | 21.8119 | 0 | 6.3458 | 1 | 1.4103 | 909.6358 | 764.1636 | 909.6358 | 0 | 145.4722 | 1 | 1.1904 | 0.57063 | 1.0017 | 1102.9683 | 957.1635 | 145.8048 | 79.84% | 82.47%
7400 Health Physics Support (Stevenson) | 20.4677 | 78.2672 | 20.4677 | 0 | -57.7995 | 1 | 0.26151 | 2267.4275 | 1972.981 | 2267.4275 | 0 | 294.4465 | 1 | 1.1492 | 0.38124 | 0.74966 | 2448.846 | 2214.981 | 233.865 | 89.07% | 92.59%
7710 NSTX-U HP and Other Allocations (Strykowsky) | 31.562 | 59.3507 | 31.562 | 0 | -27.7887 | 1 | 0.53179 | 2567.4111 | 2334.7589 | 2567.4111 | 0 | 232.6522 | 1 | 1.0996 | 0.54596 | 1.3322 | 2847.1651 | 2544.7589 | 302.4062 | 91.75% | 90.17%
7900 Integrated System (Gentile) | 6.6053 | 0 | 0.1588 | -6.4465 | 0.1588 | 0.024041 | - | 28.6497 | 3.9563 | 9.6032 | -19.0465 | 5.6469 | 0.33519 | 2.4273 | 0.9239 | 0.99362 | 78.163 | 72.9563 | 5.2067 | 5.423% | 12.29%
1.8 Site Preparation and Torus Assembly | 103.245 | 208.9036 | 142.783 | 39.538 | -66.1206 | 1.383 | 0.68349 | 6884.639 | 5882.54 | 6875.1099 | -9.5291 | 992.5699 | 0.99862 | 1.1687 | 0.76285 | 0.84625 | 10068.0128 | 9655.5401 | 412.4727 | 60.92% | 68.29%
8200 CS & Coil Supt Struct Install (Perry) | 62.7099 | 134.637 | 70.421 | 7.7111 | -64.216 | 1.123 | 0.52304 | 5423.6311 | 4846.7487 | 5427.0867 | 3.4556 | 580.338 | 1.0006 | 1.1197 | 0.74871 | 0.74884 | 7156.1695 | 7155.7487 | 0.4208 | 67.73% | 75.84%
8210 Field Supervision & Oversight (Perry) | 21.6637 | 30.0817 | 21.6637 | 0 | -8.418 | 1 | 0.72016 | 1166.2755 | 984.0486 | 1166.2755 | 0 | 182.2269 | 1 | 1.1852 | 0.58813 | 1.0008 | 1426.484 | 1244.0486 | 182.4354 | 79.1% | 81.76%
8250 Remove/Install Centerstack (Perry) | 18.8714 | 44.1849 | 50.6983 | 31.8269 | 6.5134 | 2.6865 | 1.1474 | 294.7324 | 51.7427 | 281.7477 | -12.9847 | 230.005 | 0.95594 | 5.4452 | 0.83956 | 0.99968 | 1485.3593 | 1255.7428 | 229.6165 | 4.12% | 18.97%
PMB | 1871.9026 | 1851.5173 | 1214.8927 | -657.0099 | -636.6246 | 0.64901 | 0.65616 | 73576.0713 | 71185.3177 | 69407.5809 | -4168.4904 | -1777.7368 | 0.94334 | 0.97503 | 1.1138 | 0.91267 | 86810.293 | 90253.1804 | -3442.8874 | 78.87% | 79.95%
Management Reserve | [16 empty] | 0 | -1000 | Rate adjust
TAB |  |  |  |  | < -10 K | [6 empty] | Negative Variance Threshold tripped |  |  |  |  | 86810.293 | 89253.1804
[5 empty] | >10K | [6 empty] | Positive Variance Threshold tripped |  |  |  |  | BCWR (=pmb-bcwp) | ETC (=EAC-acwp)
[17 empty] | 17402.7121 | 18067.8627
[16 empty] | contingency remaining (94,300-acwp-BCWR)= | 5711.9702
[16 empty] | contingency remaining (94,300-acwp-ETC)= |  | 5046.8196
[17 empty] | 32.82% | 27.93%

## Template
<Header>{Report} |  | Current Period | [6 empty] | Cumulative to Date | [8 empty] | At Complete
<Header>{Page} | {=SUBSTITUTE("ReportOptions.Criteria", ", ", CHAR(10))} | {Term.Budget} | {Term.Actual} | {Term.Earned} | SV | CV | SPI | CPI | {Term.Budget} | {Term.Actual} | {Term.Earned} | SV | CV | SPI | CPI | TCPIbac | TCPIeac | {Term.BAC} | {Term.EAC} | VAC | % Spent | % Complete | Original {Term.BAC} | Original {Term.EAC} | {Term.BAC} Changes | {Term.EAC} Changes
<Header>{CriteriaN}{Group} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} | {CostSet1.Period2.Value} | {CostSet3.Period2.Value} | {CostSet2.Period2.Value} | {=IF(Cell[R,C-1] = 0,"-",Cell[R,C-1]-Cell[R,C-3])}{HIGHLIGHT(Cell[R,C-3],S,P,C15)} | {=IF(Cell[R,C-2] = 0,"-",Cell[R,C-2]-Cell[R,C-3])}{HIGHLIGHT(Cell[R,C-2],C,P,C15)} | {=IF(Cell[R,C-5] = 0,"-",Cell[R,C-3]/Cell[R,C-5])} | {=IF(Cell[R,C-5] = 0,"-",Cell[R,C-4]/Cell[R,C-5])} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=IF(Cell[R,C-1] = 0,"-",Cell[R,C-1]-Cell[R,C-3])}{HIGHLIGHT(Cell[R,C-3],S,C,C15)} | {=IF(Cell[R,C-2] = 0,"-",Cell[R,C-2]-Cell[R,C-3])}{HIGHLIGHT(Cell[R,C-2],C,C,C15)} | {=IF(Cell[R,C-5] = 0,"-",Cell[R,C-3]/Cell[R,C-5])} | {=IF(Cell[R,C-5] = 0,"-",Cell[R,C-4]/Cell[R,C-5])} | #VALUE! | #VALUE! | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,C15)} | #VALUE! | #VALUE! | {CostSet5.Period2.Value} | {CostSet6.Period2.Value} | #VALUE! | #VALUE!
<Footer>{Report}{SubTotal} | PMB | {Column.Total} | {Column.Total} | {Column.Total} | {=IF(Cell[R,C-1] = 0,"-",Cell[R,C-1]-Cell[R,C-3])}{HIGHLIGHT(Cell[R,C-3],S,P,C15)} | {=IF(Cell[R,C-2] = 0,"-",Cell[R,C-2]-Cell[R,C-3])}{HIGHLIGHT(Cell[R,C-2],C,P,C15)} | {=IF(Cell[R,C-5] = 0,"-",Cell[R,C-3]/Cell[R,C-5])} | {=IF(Cell[R,C-5] = 0,"-",Cell[R,C-4]/Cell[R,C-5])}{HIGHLIGHT(Cell[R,C-2],C,P,C14)} | {Column.Total} | {Column.Total} | {Column.Total} | {=IF(Cell[R,C-1] = 0,"-",Cell[R,C-1]-Cell[R,C-3])}{HIGHLIGHT(Cell[R,C-3],S,C,C15)} | {=IF(Cell[R,C-2] = 0,"-",Cell[R,C-2]-Cell[R,C-3])}{HIGHLIGHT(Cell[R,C-2],C,C,C15)} | {=IF(Cell[R,C-5] = 0,"-",Cell[R,C-3]/Cell[R,C-5])} | {=IF(Cell[R,C-5] = 0,"-",Cell[R,C-4]/Cell[R,C-5])} | #VALUE! | #VALUE! | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,C15)} | #VALUE! | #VALUE! | {Column.Total} | {Column.Total} | #VALUE! | #VALUE!
<Footer>{BaselineLog} | Management Reserve | [16 empty] | {CostProject.Mr} | {CostProject.EstMr}
<Footer>{Report} | TAB | [16 empty] | {=Cell[R-2,C]+Cell[R-1,C]} | {=Cell[R-2,C]+Cell[R-1,C]}
<Footer>{Report}
<Footer>{Report} | Currency reported in: {ReportSetting.ScaleCaption}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
|  | Dollar | Percent | Both
|  | $ | % | Both

## Calendar
Date | 18 Label | Hours
2013-07-31 | PREVIOUS | 8880
2013-08-31 | TODATE | 176
2020-12-31 | ATCOMPLETE | 15112

## Thresholds
Code File | Code | Threshold CV Value At Complete Favorable | Threshold CV Value At Complete Unfavorable | Threshold CV % At Complete Favorable | Threshold CV % At Complete Unfavorable | Threshold CV Value Cumulative Favorable | Threshold CV Value Cumulative Unfavorable | Threshold CV % Cumulative Favorable | Threshold CV % Cumulative Unfavorable | Threshold CV Value Current Period Favorable | Threshold CV Value Current Period Unfavorable | Threshold CV % Current Period Favorable | Threshold CV % Current Period Unfavorable | Threshold SV Value Cumulative Favorable | Threshold SV Value Cumulative Unfavorable | Threshold SV % Cumulative Favorable | Threshold SV % Cumulative Unfavorable | Threshold SV Value Current Period Favorable | Threshold SV Value Current Period Unfavorable | Threshold SV % Current Period Favorable | Threshold SV % Current Period Unfavorable
NSTXUWBS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0
NSTXUWBS | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0
NSTXUWBS | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0
NSTXUWBS | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0
NSTXUWBS | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0
NSTXUWBS | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0
NSTXUWBS | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0
NSTXUWBS | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0
NSTXUWBS | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0
NSTXUOBS | 1000 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1001 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1002 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1200 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1300 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1301 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1302 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1303 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1304 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1305 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1306 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1307 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 1310 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2300 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2420 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2425 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2430 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2440 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2450 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2460 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2470 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2475 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2480 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2485 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 2490 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 3200 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 3300 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 3400 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 4100 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 4500 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 5000 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 5200 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 5501 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 6100 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 7100 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 7200 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 7300 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 7400 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 7710 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 7900 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 8200 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 8210 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | 8250 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | CS | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | NB | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | NU | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
NSTXUOBS | PM | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10

## Data
WBS | OBS | Cost Set | Date | Value | Currency
1.1 | 1000 | BCWS | 2013-07-31 | 472.3184 | TRUE
1.1 | 1000 | BCWS | 2013-08-31 | 16.9865 | TRUE
1.1 | 1000 | BCWS | 2020-12-31 | 215.9806 | TRUE
1.1 | 1000 | BCWP | 2013-07-31 | 472.3184 | TRUE
1.1 | 1000 | BCWP | 2013-08-31 | 16.9865 | TRUE
1.1 | 1000 | ACWP | 2013-07-31 | 501.302 | TRUE
1.1 | 1000 | ACWP | 2013-08-31 | 8.7936 | TRUE
1.1 | 1000 | EAC | 2013-07-31 | 501.302 | TRUE
1.1 | 1000 | EAC | 2013-08-31 | 26.4218 | TRUE
1.1 | 1000 | EAC | 2020-12-31 | 214.7436 | TRUE
1.1 | 1001 | BCWS | 2013-07-31 | 1949.4457 | TRUE
1.1 | 1001 | BCWS | 2013-08-31 | 1.9313 | TRUE
1.1 | 1001 | BCWS | 2020-12-31 | 158.6116 | TRUE
1.1 | 1001 | BCWP | 2013-07-31 | 1816.4273 | TRUE
1.1 | 1001 | BCWP | 2013-08-31 | 33.3772 | TRUE
1.1 | 1001 | ACWP | 2013-07-31 | 1529.2985 | TRUE
1.1 | 1001 | ACWP | 2013-08-31 | 107.2683 | TRUE
1.1 | 1001 | EAC | 2013-07-31 | 1529.2985 | TRUE
1.1 | 1001 | EAC | 2013-08-31 | 142.0424 | TRUE
1.1 | 1001 | EAC | 2020-12-31 | 259.2258 | TRUE
1.1 | 1002 | BCWS | 2013-07-31 | 639.1518 | TRUE
1.1 | 1002 | BCWP | 2013-07-31 | 605.3577 | TRUE
1.1 | 1002 | BCWP | 2013-08-31 | 34.0082 | TRUE
1.1 | 1002 | ACWP | 2013-07-31 | 501.3276 | TRUE
1.1 | 1002 | ACWP | 2013-08-31 | 12.3861 | TRUE
1.1 | 1002 | EAC | 2013-07-31 | 501.3276 | TRUE
1.1 | 1002 | EAC | 2013-08-31 | 448.2611 | TRUE
1.1 | 1002 | EAC | 2020-12-31 | 198.125 | TRUE
1.1 | 1200 | BCWS | 2013-07-31 | 3673.291 | TRUE
1.1 | 1200 | BCWS | 2013-08-31 | 10.1672 | TRUE
1.1 | 1200 | BCWS | 2020-12-31 | 107.0614 | TRUE
1.1 | 1200 | BCWP | 2013-07-31 | 3699.3411 | TRUE
1.1 | 1200 | BCWP | 2013-08-31 | 0.3543 | TRUE
1.1 | 1200 | ACWP | 2013-07-31 | 4367.3826 | TRUE
1.1 | 1200 | ACWP | 2013-08-31 | 0.4139 | TRUE
1.1 | 1200 | EAC | 2013-07-31 | 4367.3826 | TRUE
1.1 | 1200 | EAC | 2013-08-31 | 44.9255 | TRUE
1.1 | 1200 | EAC | 2020-12-31 | 42.4884 | TRUE
1.1 | 1300 | BCWS | 2013-07-31 | 1882.148 | TRUE
1.1 | 1300 | BCWS | 2013-08-31 | 139.681 | TRUE
1.1 | 1300 | BCWS | 2020-12-31 | 249.971 | TRUE
1.1 | 1300 | BCWP | 2013-07-31 | 1882.148 | TRUE
1.1 | 1300 | BCWP | 2013-08-31 | 139.681 | TRUE
1.1 | 1300 | ACWP | 2013-07-31 | 2083.3932 | TRUE
1.1 | 1300 | ACWP | 2013-08-31 | 117.1547 | TRUE
1.1 | 1300 | EAC | 2013-07-31 | 2083.3932 | TRUE
1.1 | 1300 | EAC | 2013-08-31 | 461.8214 | TRUE
1.1 | 1300 | EAC | 2020-12-31 | 313.3333 | TRUE
1.1 | 1301 | BCWS | 2013-07-31 | 470.5301 | TRUE
1.1 | 1301 | BCWP | 2013-07-31 | 470.5301 | TRUE
1.1 | 1301 | ACWP | 2013-07-31 | 485.4711 | TRUE
1.1 | 1301 | ACWP | 2013-08-31 | -100.6602 | TRUE
1.1 | 1301 | EAC | 2013-07-31 | 485.4711 | TRUE
1.1 | 1301 | EAC | 2013-08-31 | -100.6602 | TRUE
1.1 | 1302 | BCWS | 2013-07-31 | 326.9323 | TRUE
1.1 | 1302 | BCWS | 2013-08-31 | 85.4741 | TRUE
1.1 | 1302 | BCWS | 2020-12-31 | 432.1384 | TRUE
1.1 | 1302 | BCWP | 2013-07-31 | 78.1395 | TRUE
1.1 | 1302 | BCWP | 2013-08-31 | 38.2363 | TRUE
1.1 | 1302 | ACWP | 2013-07-31 | 60.3954 | TRUE
1.1 | 1302 | ACWP | 2013-08-31 | 64.7973 | TRUE
1.1 | 1302 | EAC | 2013-07-31 | 60.3954 | TRUE
1.1 | 1302 | EAC | 2013-08-31 | 165.0332 | TRUE
1.1 | 1302 | EAC | 2020-12-31 | 710.764 | TRUE
1.1 | 1303 | BCWS | 2013-07-31 | 352.8769 | TRUE
1.1 | 1303 | BCWP | 2013-07-31 | 352.8769 | TRUE
1.1 | 1303 | ACWP | 2013-07-31 | 225.084 | TRUE
1.1 | 1303 | EAC | 2013-07-31 | 224.5695 | TRUE
1.1 | 1304 | BCWS | 2013-07-31 | 2778.8928 | TRUE
1.1 | 1304 | BCWS | 2020-12-31 | 786.7949 | TRUE
1.1 | 1304 | BCWP | 2013-07-31 | 2986.2566 | TRUE
1.1 | 1304 | BCWP | 2013-08-31 | 56.8146 | TRUE
1.1 | 1304 | ACWP | 2013-07-31 | 3084.571 | TRUE
1.1 | 1304 | ACWP | 2013-08-31 | 54.7586 | TRUE
1.1 | 1304 | EAC | 2013-07-31 | 3084.571 | TRUE
1.1 | 1304 | EAC | 2013-08-31 | 215.9991 | TRUE
1.1 | 1304 | EAC | 2020-12-31 | 417.7595 | TRUE
1.1 | 1305 | BCWS | 2013-07-31 | 5866.1495 | TRUE
1.1 | 1305 | BCWS | 2013-08-31 | 135.4608 | TRUE
1.1 | 1305 | BCWS | 2020-12-31 | 409.1804 | TRUE
1.1 | 1305 | BCWP | 2013-07-31 | 5417.0505 | TRUE
1.1 | 1305 | BCWP | 2013-08-31 | 127.7721 | TRUE
1.1 | 1305 | ACWP | 2013-07-31 | 7799.146 | TRUE
1.1 | 1305 | ACWP | 2013-08-31 | 331.4722 | TRUE
1.1 | 1305 | EAC | 2013-07-31 | 7799.146 | TRUE
1.1 | 1305 | EAC | 2013-08-31 | 497.1109 | TRUE
1.1 | 1305 | EAC | 2020-12-31 | 1001.3613 | TRUE
1.1 | 1306 | BCWS | 2013-07-31 | 610.9485 | TRUE
1.1 | 1306 | BCWS | 2013-08-31 | 71.5789 | TRUE
1.1 | 1306 | BCWS | 2020-12-31 | 141.5506 | TRUE
1.1 | 1306 | BCWP | 2013-07-31 | 380.2693 | TRUE
1.1 | 1306 | ACWP | 2013-07-31 | 542.3895 | TRUE
1.1 | 1306 | ACWP | 2013-08-31 | 12.3008 | TRUE
1.1 | 1306 | EAC | 2013-07-31 | 625.1692 | TRUE
1.1 | 1306 | EAC | 2013-08-31 | 95.0805 | TRUE
1.1 | 1306 | EAC | 2020-12-31 | 278.4407 | TRUE
1.1 | 1307 | BCWS | 2013-07-31 | 1360.7292 | TRUE
1.1 | 1307 | BCWS | 2020-12-31 | 23.085 | TRUE
1.1 | 1307 | BCWP | 2013-07-31 | 1130.7325 | TRUE
1.1 | 1307 | BCWP | 2013-08-31 | 85.615 | TRUE
1.1 | 1307 | ACWP | 2013-07-31 | 1175.6083 | TRUE
1.1 | 1307 | ACWP | 2013-08-31 | 65.5704 | TRUE
1.1 | 1307 | EAC | 2013-07-31 | 1175.6083 | TRUE
1.1 | 1307 | EAC | 2013-08-31 | 105.8781 | TRUE
1.1 | 1307 | EAC | 2020-12-31 | 221.6923 | TRUE
1.1 | 1310 | BCWS | 2013-07-31 | 441.918 | TRUE
1.1 | 1310 | BCWP | 2013-07-31 | 441.918 | TRUE
1.1 | 1310 | ACWP | 2013-07-31 | 441.9189 | TRUE
1.1 | 1310 | EAC | 2013-07-31 | 441.9189 | TRUE
1.2 | 2300 | BCWS | 2013-07-31 | 84.1986 | TRUE
1.2 | 2300 | BCWP | 2013-07-31 | 84.1986 | TRUE
1.2 | 2300 | ACWP | 2013-07-31 | 28.7168 | TRUE
1.2 | 2300 | EAC | 2013-07-31 | 29.0946 | TRUE
1.2 | 2420 | BCWS | 2013-07-31 | 80.5268 | TRUE
1.2 | 2420 | BCWS | 2013-08-31 | 60.2675 | TRUE
1.2 | 2420 | BCWS | 2020-12-31 | -41.5989 | TRUE
1.2 | 2420 | BCWP | 2013-07-31 | 99.1954 | TRUE
1.2 | 2420 | ACWP | 2013-07-31 | 61.3631 | TRUE
1.2 | 2420 | EAC | 2013-07-31 | 61.3631 | TRUE
1.2 | 2425 | BCWS | 2013-07-31 | 1802.8764 | TRUE
1.2 | 2425 | BCWP | 2013-07-31 | 1584.2717 | TRUE
1.2 | 2425 | BCWP | 2013-08-31 | 16.9957 | TRUE
1.2 | 2425 | ACWP | 2013-07-31 | 1130.1209 | TRUE
1.2 | 2425 | ACWP | 2013-08-31 | 6.2689 | TRUE
1.2 | 2425 | EAC | 2013-07-31 | 1130.1209 | TRUE
1.2 | 2425 | EAC | 2013-08-31 | 32.1722 | TRUE
1.2 | 2425 | EAC | 2020-12-31 | 193.0968 | TRUE
1.2 | 2430 | BCWS | 2013-07-31 | 2057.0497 | TRUE
1.2 | 2430 | BCWP | 2013-07-31 | 2057.0497 | TRUE
1.2 | 2430 | ACWP | 2013-07-31 | 2069.9356 | TRUE
1.2 | 2430 | EAC | 2013-07-31 | 2069.9356 | TRUE
1.2 | 2440 | BCWS | 2013-07-31 | 1978.776 | TRUE
1.2 | 2440 | BCWP | 2013-07-31 | 1901.1671 | TRUE
1.2 | 2440 | ACWP | 2013-07-31 | 1486.3013 | TRUE
1.2 | 2440 | ACWP | 2013-08-31 | 24.3082 | TRUE
1.2 | 2440 | EAC | 2013-07-31 | 1486.3013 | TRUE
1.2 | 2440 | EAC | 2013-08-31 | 31.2555 | TRUE
1.2 | 2440 | EAC | 2020-12-31 | 71.0526 | TRUE
1.2 | 2450 | BCWS | 2013-07-31 | 2221.712 | TRUE
1.2 | 2450 | BCWS | 2013-08-31 | 675.6571 | TRUE
1.2 | 2450 | BCWS | 2020-12-31 | 2053.0653 | TRUE
1.2 | 2450 | BCWP | 2013-07-31 | 2710.9153 | TRUE
1.2 | 2450 | BCWP | 2013-08-31 | 467.9157 | TRUE
1.2 | 2450 | ACWP | 2013-07-31 | 2487.0991 | TRUE
1.2 | 2450 | ACWP | 2013-08-31 | 338.4679 | TRUE
1.2 | 2450 | EAC | 2013-07-31 | 2487.0991 | TRUE
1.2 | 2450 | EAC | 2013-08-31 | 638.9557 | TRUE
1.2 | 2450 | EAC | 2020-12-31 | 1939.5122 | TRUE
1.2 | 2460 | BCWS | 2013-07-31 | 506.4187 | TRUE
1.2 | 2460 | BCWS | 2013-08-31 | 3.477 | TRUE
1.2 | 2460 | BCWS | 2020-12-31 | 250.6494 | TRUE
1.2 | 2460 | BCWP | 2013-07-31 | 652.4475 | TRUE
1.2 | 2460 | ACWP | 2013-07-31 | 876.0661 | TRUE
1.2 | 2460 | ACWP | 2013-08-31 | 2.2042 | TRUE
1.2 | 2460 | EAC | 2013-07-31 | 888.9791 | TRUE
1.2 | 2460 | EAC | 2013-08-31 | 15.1172 | TRUE
1.2 | 2460 | EAC | 2020-12-31 | 82.1739 | TRUE
1.2 | 2470 | BCWS | 2013-07-31 | 1129.856 | TRUE
1.2 | 2470 | BCWS | 2013-08-31 | 187.0755 | TRUE
1.2 | 2470 | BCWS | 2020-12-31 | 2017.9449 | TRUE
1.2 | 2470 | BCWP | 2013-07-31 | 1105.4545 | TRUE
1.2 | 2470 | BCWP | 2013-08-31 | 1.7602 | TRUE
1.2 | 2470 | ACWP | 2013-07-31 | 1233.5164 | TRUE
1.2 | 2470 | ACWP | 2013-08-31 | 57.2056 | TRUE
1.2 | 2470 | EAC | 2013-07-31 | 1233.5164 | TRUE
1.2 | 2470 | EAC | 2013-08-31 | 268.2819 | TRUE
1.2 | 2470 | EAC | 2020-12-31 | 2177.9237 | TRUE
1.2 | 2475 | BCWS | 2013-07-31 | 1919.3409 | TRUE
1.2 | 2475 | BCWS | 2013-08-31 | 60.3307 | TRUE
1.2 | 2475 | BCWS | 2020-12-31 | 631.5841 | TRUE
1.2 | 2475 | BCWP | 2013-07-31 | 1681.8566 | TRUE
1.2 | 2475 | ACWP | 2013-07-31 | 1352.0766 | TRUE
1.2 | 2475 | ACWP | 2013-08-31 | 19.0473 | TRUE
1.2 | 2475 | EAC | 2013-07-31 | 1484.7909 | TRUE
1.2 | 2475 | EAC | 2013-08-31 | 88.5643 | TRUE
1.2 | 2475 | EAC | 2020-12-31 | 726.7687 | TRUE
1.2 | 2480 | BCWS | 2013-07-31 | 1597.1689 | TRUE
1.2 | 2480 | BCWS | 2013-08-31 | 154.0215 | TRUE
1.2 | 2480 | BCWS | 2020-12-31 | 342.8121 | TRUE
1.2 | 2480 | BCWP | 2013-07-31 | 1778.2303 | TRUE
1.2 | 2480 | BCWP | 2013-08-31 | 102.5475 | TRUE
1.2 | 2480 | ACWP | 2013-07-31 | 2155.9153 | TRUE
1.2 | 2480 | ACWP | 2013-08-31 | 62.6083 | TRUE
1.2 | 2480 | EAC | 2013-07-31 | 2155.9153 | TRUE
1.2 | 2480 | EAC | 2013-08-31 | 81.4996 | TRUE
1.2 | 2480 | EAC | 2020-12-31 | 297.1087 | TRUE
1.2 | 2485 | BCWS | 2013-07-31 | 90.3197 | TRUE
1.2 | 2485 | BCWS | 2020-12-31 | 297.4007 | TRUE
1.2 | 2485 | BCWP | 2013-07-31 | 291.2918 | TRUE
1.2 | 2485 | ACWP | 2013-07-31 | 358.5749 | TRUE
1.2 | 2485 | ACWP | 2013-08-31 | 2.9211 | TRUE
1.2 | 2485 | EAC | 2013-07-31 | 358.5749 | TRUE
1.2 | 2485 | EAC | 2013-08-31 | 25.1527 | TRUE
1.2 | 2485 | EAC | 2020-12-31 | 73.7684 | TRUE
1.2 | 2490 | BCWS | 2013-07-31 | 1847.2259 | TRUE
1.2 | 2490 | BCWS | 2013-08-31 | 29.9287 | TRUE
1.2 | 2490 | BCWS | 2020-12-31 | 1433.8968 | TRUE
1.2 | 2490 | BCWP | 2013-07-31 | 1857.4168 | TRUE
1.2 | 2490 | ACWP | 2013-07-31 | 1967.5453 | TRUE
1.2 | 2490 | ACWP | 2013-08-31 | 68.3821 | TRUE
1.2 | 2490 | EAC | 2013-07-31 | 1967.5453 | TRUE
1.2 | 2490 | EAC | 2013-08-31 | 182.1401 | TRUE
1.2 | 2490 | EAC | 2020-12-31 | 1339.242 | TRUE
1.3 | 3200 | BCWS | 2013-07-31 | 74.1034 | TRUE
1.3 | 3200 | BCWS | 2020-12-31 | 121.1333 | TRUE
1.3 | 3200 | BCWP | 2013-07-31 | 68.0914 | TRUE
1.3 | 3200 | ACWP | 2013-07-31 | 37.6091 | TRUE
1.3 | 3200 | EAC | 2013-07-31 | 93.0027 | TRUE
1.3 | 3200 | EAC | 2013-08-31 | 7.4309 | TRUE
1.3 | 3200 | EAC | 2020-12-31 | 64.1755 | TRUE
1.3 | 3300 | BCWS | 2013-07-31 | 4.7648 | TRUE
1.3 | 3300 | BCWS | 2020-12-31 | 74.417 | TRUE
1.3 | 3300 | BCWP | 2013-07-31 | 54.7726 | TRUE
1.3 | 3300 | ACWP | 2013-07-31 | 43.828 | TRUE
1.3 | 3300 | ACWP | 2013-08-31 | 6.1738 | TRUE
1.3 | 3300 | EAC | 2013-07-31 | 43.828 | TRUE
1.3 | 3300 | EAC | 2013-08-31 | 21.8405 | TRUE
1.3 | 3300 | EAC | 2020-12-31 | 78.3333 | TRUE
1.3 | 3400 | BCWS | 2013-07-31 | 41.0294 | TRUE
1.3 | 3400 | BCWS | 2020-12-31 | 61.2594 | TRUE
1.3 | 3400 | BCWP | 2013-07-31 | 47.6224 | TRUE
1.3 | 3400 | BCWP | 2013-08-31 | 8.4305 | TRUE
1.3 | 3400 | ACWP | 2013-07-31 | 59.4609 | TRUE
1.3 | 3400 | ACWP | 2013-08-31 | 9.0878 | TRUE
1.3 | 3400 | EAC | 2013-07-31 | 72.613 | TRUE
1.3 | 3400 | EAC | 2013-08-31 | 22.24 | TRUE
1.3 | 3400 | EAC | 2020-12-31 | 28.6957 | TRUE
1.4 | 4100 | BCWS | 2013-07-31 | 792.1927 | TRUE
1.4 | 4100 | BCWS | 2013-08-31 | 43.3969 | TRUE
1.4 | 4100 | BCWP | 2013-07-31 | 694.9038 | TRUE
1.4 | 4100 | BCWP | 2013-08-31 | 11.4002 | TRUE
1.4 | 4100 | ACWP | 2013-07-31 | 559.3949 | TRUE
1.4 | 4100 | ACWP | 2013-08-31 | 22.4766 | TRUE
1.4 | 4100 | EAC | 2013-07-31 | 559.3949 | TRUE
1.4 | 4100 | EAC | 2013-08-31 | 57.3305 | TRUE
1.4 | 4100 | EAC | 2020-12-31 | 106.1461 | TRUE
1.4 | 4500 | BCWS | 2013-07-31 | 1127.6562 | TRUE
1.4 | 4500 | BCWS | 2013-08-31 | 2.5008 | TRUE
1.4 | 4500 | BCWS | 2020-12-31 | 6.5004 | TRUE
1.4 | 4500 | BCWP | 2013-07-31 | 1030.6938 | TRUE
1.4 | 4500 | BCWP | 2013-08-31 | 20.0451 | TRUE
1.4 | 4500 | ACWP | 2013-07-31 | 1400.0426 | TRUE
1.4 | 4500 | ACWP | 2013-08-31 | 25.7537 | TRUE
1.4 | 4500 | EAC | 2013-07-31 | 1400.0426 | TRUE
1.4 | 4500 | EAC | 2013-08-31 | 189.0614 | TRUE
1.4 | 4500 | EAC | 2020-12-31 | 29.6923 | TRUE
1.5 | 5000 | BCWS | 2013-07-31 | 2699.422 | TRUE
1.5 | 5000 | BCWS | 2013-08-31 | 165.6513 | TRUE
1.5 | 5000 | BCWS | 2020-12-31 | 2870.4182 | TRUE
1.5 | 5000 | BCWP | 2013-07-31 | 3121.7145 | TRUE
1.5 | 5000 | BCWP | 2013-08-31 | 124.3618 | TRUE
1.5 | 5000 | ACWP | 2013-07-31 | 2621.858 | TRUE
1.5 | 5000 | ACWP | 2013-08-31 | 49.5484 | TRUE
1.5 | 5000 | EAC | 2013-07-31 | 2621.858 | TRUE
1.5 | 5000 | EAC | 2013-08-31 | 246.5519 | TRUE
1.5 | 5000 | EAC | 2020-12-31 | 2372.9965 | TRUE
1.5 | 5200 | BCWS | 2013-07-31 | 1728.5767 | TRUE
1.5 | 5200 | BCWS | 2013-08-31 | 158.2026 | TRUE
1.5 | 5200 | BCWS | 2020-12-31 | 519.6035 | TRUE
1.5 | 5200 | BCWP | 2013-07-31 | 1411.6388 | TRUE
1.5 | 5200 | BCWP | 2013-08-31 | 90.2969 | TRUE
1.5 | 5200 | ACWP | 2013-07-31 | 1918.1293 | TRUE
1.5 | 5200 | ACWP | 2013-08-31 | 186.4943 | TRUE
1.5 | 5200 | EAC | 2013-07-31 | 1918.1293 | TRUE
1.5 | 5200 | EAC | 2013-08-31 | 261.9771 | TRUE
1.5 | 5200 | EAC | 2020-12-31 | 919.5172 | TRUE
1.5 | 5501 | BCWS | 2013-07-31 | 993.1035 | TRUE
1.5 | 5501 | BCWS | 2013-08-31 | 62.996 | TRUE
1.5 | 5501 | BCWS | 2020-12-31 | 849.4844 | TRUE
1.5 | 5501 | BCWP | 2013-07-31 | 634.4121 | TRUE
1.5 | 5501 | BCWP | 2013-08-31 | 95.228 | TRUE
1.5 | 5501 | ACWP | 2013-07-31 | 628.507 | TRUE
1.5 | 5501 | ACWP | 2013-08-31 | 89.1324 | TRUE
1.5 | 5501 | EAC | 2013-07-31 | 628.507 | TRUE
1.5 | 5501 | EAC | 2013-08-31 | 204.9176 | TRUE
1.5 | 5501 | EAC | 2020-12-31 | 1305.2148 | TRUE
1.6 | 6100 | BCWS | 2013-07-31 | 214.1047 | TRUE
1.6 | 6100 | BCWS | 2013-08-31 | 7.7754 | TRUE
1.6 | 6100 | BCWS | 2020-12-31 | 734.2114 | TRUE
1.6 | 6100 | BCWP | 2013-07-31 | 348.2209 | TRUE
1.6 | 6100 | BCWP | 2013-08-31 | 5.6908 | TRUE
1.6 | 6100 | ACWP | 2013-07-31 | 315.8973 | TRUE
1.6 | 6100 | ACWP | 2013-08-31 | 1.334 | TRUE
1.6 | 6100 | EAC | 2013-07-31 | 315.8973 | TRUE
1.6 | 6100 | EAC | 2013-08-31 | 57.3258 | TRUE
1.6 | 6100 | EAC | 2020-12-31 | 565.0082 | TRUE
1.7 | 7100 | BCWS | 2013-07-31 | 4939.3056 | TRUE
1.7 | 7100 | BCWS | 2013-08-31 | 91.0402 | TRUE
1.7 | 7100 | BCWS | 2020-12-31 | 1381.7146 | TRUE
1.7 | 7100 | BCWP | 2013-07-31 | 4939.3056 | TRUE
1.7 | 7100 | BCWP | 2013-08-31 | 91.0402 | TRUE
1.7 | 7100 | ACWP | 2013-07-31 | 5159.9364 | TRUE
1.7 | 7100 | ACWP | 2013-08-31 | 102.9645 | TRUE
1.7 | 7100 | EAC | 2013-07-31 | 5159.9364 | TRUE
1.7 | 7100 | EAC | 2013-08-31 | 244.284 | TRUE
1.7 | 7100 | EAC | 2020-12-31 | 1708.6806 | TRUE
1.7 | 7200 | BCWS | 2013-07-31 | 1256.2132 | TRUE
1.7 | 7200 | BCWS | 2013-08-31 | 73.289 | TRUE
1.7 | 7200 | BCWS | 2020-12-31 | 294.2935 | TRUE
1.7 | 7200 | BCWP | 2013-07-31 | 1256.2132 | TRUE
1.7 | 7200 | BCWP | 2013-08-31 | 18.3756 | TRUE
1.7 | 7200 | ACWP | 2013-07-31 | 1125.0657 | TRUE
1.7 | 7200 | ACWP | 2013-08-31 | 13.8855 | TRUE
1.7 | 7200 | EAC | 2013-07-31 | 1125.0657 | TRUE
1.7 | 7200 | EAC | 2013-08-31 | 42.9034 | TRUE
1.7 | 7200 | EAC | 2020-12-31 | 338.9821 | TRUE
1.7 | 7300 | BCWS | 2013-07-31 | 805.3961 | TRUE
1.7 | 7300 | BCWS | 2013-08-31 | 21.3422 | TRUE
1.7 | 7300 | BCWS | 2020-12-31 | 276.2299 | TRUE
1.7 | 7300 | BCWP | 2013-07-31 | 805.3961 | TRUE
1.7 | 7300 | BCWP | 2013-08-31 | 21.3422 | TRUE
1.7 | 7300 | ACWP | 2013-07-31 | 698.6663 | TRUE
1.7 | 7300 | ACWP | 2013-08-31 | 9.8066 | TRUE
1.7 | 7300 | EAC | 2013-07-31 | 698.6663 | TRUE
1.7 | 7300 | EAC | 2013-08-31 | 32.4156 | TRUE
1.7 | 7300 | EAC | 2020-12-31 | 274.391 | TRUE
1.7 | 7400 | BCWS | 2013-07-31 | 2143.3105 | TRUE
1.7 | 7400 | BCWS | 2013-08-31 | 31.3339 | TRUE
1.7 | 7400 | BCWS | 2020-12-31 | 274.2017 | TRUE
1.7 | 7400 | BCWP | 2013-07-31 | 2143.3105 | TRUE
1.7 | 7400 | BCWP | 2013-08-31 | 31.3339 | TRUE
1.7 | 7400 | ACWP | 2013-07-31 | 1631.7253 | TRUE
1.7 | 7400 | ACWP | 2013-08-31 | 66.161 | TRUE
1.7 | 7400 | EAC | 2013-07-31 | 1631.7253 | TRUE
1.7 | 7400 | EAC | 2013-08-31 | 90.2977 | TRUE
1.7 | 7400 | EAC | 2020-12-31 | 280.8633 | TRUE
1.7 | 7710 | BCWS | 2013-07-31 | 2406.5063 | TRUE
1.7 | 7710 | BCWS | 2013-08-31 | 33.8794 | TRUE
1.7 | 7710 | BCWS | 2020-12-31 | 406.7794 | TRUE
1.7 | 7710 | BCWP | 2013-07-31 | 2406.5063 | TRUE
1.7 | 7710 | BCWP | 2013-08-31 | 33.8794 | TRUE
1.7 | 7710 | ACWP | 2013-07-31 | 2103.8801 | TRUE
1.7 | 7710 | ACWP | 2013-08-31 | 22.6634 | TRUE
1.7 | 7710 | EAC | 2013-07-31 | 2103.8801 | TRUE
1.7 | 7710 | EAC | 2013-08-31 | 53.7595 | TRUE
1.7 | 7710 | EAC | 2020-12-31 | 409.9038 | TRUE
1.7 | 7900 | BCWS | 2013-07-31 | 8.8267 | TRUE
1.7 | 7900 | BCWS | 2013-08-31 | 0.1536 | TRUE
1.7 | 7900 | BCWS | 2020-12-31 | 69.1828 | TRUE
1.7 | 7900 | BCWP | 2013-07-31 | 8.8267 | TRUE
1.7 | 7900 | BCWP | 2013-08-31 | 0.1536 | TRUE
1.7 | 7900 | ACWP | 2013-07-31 | 3.9563 | TRUE
1.7 | 7900 | EAC | 2013-07-31 | 8.3691 | TRUE
1.7 | 7900 | EAC | 2013-08-31 | 4.4128 | TRUE
1.7 | 7900 | EAC | 2020-12-31 | 60.1744 | TRUE
1.8 | 8200 | BCWS | 2013-07-31 | 4370.9048 | TRUE
1.8 | 8200 | BCWS | 2013-08-31 | 244.6012 | TRUE
1.8 | 8200 | BCWS | 2020-12-31 | 2540.6635 | TRUE
1.8 | 8200 | BCWP | 2013-07-31 | 4017.3219 | TRUE
1.8 | 8200 | BCWP | 2013-08-31 | 469.0678 | TRUE
1.8 | 8200 | ACWP | 2013-07-31 | 4115.082 | TRUE
1.8 | 8200 | ACWP | 2013-08-31 | 241.4386 | TRUE
1.8 | 8200 | EAC | 2013-07-31 | 4115.082 | TRUE
1.8 | 8200 | EAC | 2013-08-31 | 479.5697 | TRUE
1.8 | 8200 | EAC | 2020-12-31 | 2900.869 | TRUE
1.8 | 8210 | BCWS | 2013-07-31 | 994.8137 | TRUE
1.8 | 8210 | BCWS | 2013-08-31 | 46.3096 | TRUE
1.8 | 8210 | BCWS | 2020-12-31 | 385.3606 | TRUE
1.8 | 8210 | BCWP | 2013-07-31 | 994.8137 | TRUE
1.8 | 8210 | BCWP | 2013-08-31 | 46.3096 | TRUE
1.8 | 8210 | ACWP | 2013-07-31 | 836.7772 | TRUE
1.8 | 8210 | ACWP | 2013-08-31 | 32.7813 | TRUE
1.8 | 8210 | EAC | 2013-07-31 | 836.7772 | TRUE
1.8 | 8210 | EAC | 2013-08-31 | 62.3202 | TRUE
1.8 | 8210 | EAC | 2020-12-31 | 401.4611 | TRUE
1.8 | 8250 | BCWS | 2013-07-31 | 210.0462 | TRUE
1.8 | 8250 | BCWS | 2013-08-31 | 26.8214 | TRUE
1.8 | 8250 | BCWS | 2020-12-31 | 985.7649 | TRUE
1.8 | 8250 | BCWP | 2013-07-31 | 169.2885 | TRUE
1.8 | 8250 | ACWP | 2013-07-31 | 1.8554 | TRUE
1.8 | 8250 | ACWP | 2013-08-31 | 0.8355 | TRUE
1.8 | 8250 | EAC | 2013-07-31 | 1.8554 | TRUE
1.8 | 8250 | EAC | 2013-08-31 | 91.4153 | TRUE
1.8 | 8250 | EAC | 2020-12-31 | 1173.4202 | TRUE