## Slide 1
Review Closeout for the
National Spherical Torus
Experiment (NSTX) Upgrade Project
Princeton Plasma Physics Laboratory
February 4, 2014

## Slide 2: Review Committee
Kin Chao, DOE/SC, Chairperson
Review Committee
Arnie Kellman, General Atomics
Will Oren, TJNAF
Observers
Barry Sullivan, DOE/SC
Tony Indelicato, DOE/PSO
Maria Dikeakos, DOE/PSO

## Slide 3: Charge Questions
Critical Path Construction Efforts: Does the Project team have a realistic, executable schedule for Center Stack (CS) remaining construction efforts?
Yes, but it remains aggressive for the early finish date.
Does the project have adequate resources and the appropriate skills mix to execute the remainder of the project per the plan? Yes.
2. Baseline Cost and Schedule: Are the current project cost and schedule projections consistent with the approved baseline cost and schedule? Yes
Is the contingency remaining adequate for the risks that remain? Yes
Management: Evaluate the management structure as to its adequacy to deliver the scope within budget and schedule. Are risks being actively managed? Yes—the structure and organization remains the same since the last review.
Has the project responded satisfactorily to the recommendations from the previous project reviews? Yes—the project responded satisfactorily to all the recommendations.

## Slide 4: Project Status
Project Status as of December 31, 2013 |  | 
Project Type | MIE | 
CD-1 | Planned: Dec 2009 | Actual: Apr 2010
CD-2 | Planned: Dec 2010 | Actual: Jan 2011
CD-3 | Planned: Jan 2012 | Actual: Dec 2011
CD-4 | Planned: Sep 2015 | Actual: on schedule
TPC Percent Complete | Planned: 84.5% | Actual: 80%
TPC Cost to Date | $71.2M | 
TPC Committed to Date | $73.2M | 
TPC | $94.3M | 
TEC | $83.5M | 
Contingency Cost (no Mgmt Reserve) | $5.4M | 30 % to go
Contingency Schedule on CD-4 | 10 months | 101%
CPI Cumulative | 0.98 | 
SPI Cumulative | 0.94 | 

## Slide 5: 2. Technical Status A. Kellman, GA*/W. Oren, TJNAF
Findings
The safety record of the project continues to be outstanding with no safety incidents reported to this committee since the last meeting.
TF coil was completed since last review and electrical tests were successfully performed.
First layer of OH has been wound on the Aquapour base with a resulting 240 turns vs planned 226 turns. The radial build is in tolerance. Production in-line braze joints have been successfully performed. Completion of the first layer-to-layer transition is in process.
Learning curve for winding is as expected and has resulted in two shift operation with 4 -man teams carrying out this work.
Both PF1B coils have fabricated and one has been delivered. The tooling for PF1A and PF1C are complete and winding of PF1A is starting.

## Slide 6: 2. Technical Status A. Kellman, GA*/W. Oren, TJNAF
Findings
Setup and commissioning of winding station took 14 weeks longer than scheduled and it pushed this task into critical path. Overall, 26 days were lost on critical path, but 24 days have been recovered in the schedule by planning for 2nd shift operation on non-winding tasks.

## Slide 7: 2. Technical Status A. Kellman, GA*/W. Oren, TJNAF
Comments
Project management has satisfactorily responded to all recommendations of the previous review. Risk registry is being updated and actively used as a tool.
OH winding process is proceeding faster than scheduled. This efficiency is being banked to allow for future slippages in OH assembly.
The project continues to demonstrate a high attention to quality, especially in the OH work that this committee was shown. The focus on quality should continue.
The project should continue proactive work planning for all remaining work.
It is of some concern that there is no firm understanding of why there are 14 extra turns in the first layer of 226 turns planned. While the higher number of turns is not a problem for the physics program, it is concerning that this may be pointing to a potentially serious design or fabrication issue and is worth resolving.

## Slide 8: 2. Technical Status A. Kellman, GA*/W. Oren, TJNAF
Recommendations
None